## Sheet1
| 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9 |  |  |  |  | 10 |  |  |  |  | 11 |  |  |  |  | 12 |  |  |  |  | 13 |  |  |  |  | 14 |  |  |  |  | 15 |  |  |  |  | 16 |  |  |  |  | 17
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Project Management
Plan the project | bar: 1 M to 1 F
Identify Resources | bar: 1 W to 1 T
Upskilling | bar: 1 M to 2 F
Gathering Background Information | bar: 1 F to 2 T
Project and Development Review | bar: 2 W to 2 F
Game UI and Frontend Design
Frontend Game Design Mock Ups | bar: 3 M to 3 W
Gamining Mechanics | bar: 3 T to 3 T
Game Design Flow | bar: 3 T to 4 M
Educational Content | bar: 4 M to 4 F
Backend/Game Logic Design
Modular Content | bar: 4 M to 4 W
Model Interaction with Game Board | bar: 4 T to 4 W
Models Input Requirements and Outputs | bar: 4 M to 4 T
Educational Content Triggers | bar: 4 T to 4 F
Implementation & Testing
Implementation | bar: 5 M to 11 F
Testing | bar: 5 M to 11 F
User Testing | bar: 12 M to 13 F
Modifications | bar: 13 M to 14 F
Documentation
Project Documentaion Write up | bar: 15 M to 17 F