## Sheet1
| 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9 |  |  |  |  | 10 |  |  |  |  | 11 |  |  |  |  | 12 |  |  |  |  | 13 |  |  |  |  | 14 |  |  |  |  | 15 |  |  |  |  | 16 |  |  |  |  | 17
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Project Management
Plan the project | bar: 1 M to 1 F
Identify Resources | bar: 1 W to 1 T
Upskilling | bar: 1 M to 10 F
Gathering Background Information | bar: 1 F to 2 T
Project and Development Review | bar: 2 W to 2 F
Web App
Frontend Design Mock Ups | bar: 2 W to 3 W
Data Capture and Database Integration | bar: 3 T to 4 T
Rating Logic | bar: 3 T to 4 T
Hosting/Deploy | bar: 4 F to 7 F
NLP Tasks
Sentiment Analysis | bar: 5 M to 5 F
Similarity Scoring | bar: 5 T to 5 F
Feature Engineering | bar: 5 M to 5 T; 6 M to 6 T
NLP Visualising | bar: 7 M to 7 T
Implementation & Testing
Implementation & NLP Exploration | bar: 3 M to 10 F
Testing (Web App + NLP) | bar: 3 M to 10 F
User Testing (Web App) | bar: 3 M to 4 F
Modifications (Web App) | bar: 3 M to 4 F
Documentation
Anysisng Results | bar: 10 M to 11 F
Project Documentaion Write up | bar: 2 M to 2 F; 4 M to 4 F; 6 M to 6 F; 8 M to 8 F; 11 M to 14 F